## Template of Project Plan DAM
Task Name | Duration | Resource | Description
0 - Kick Off - 2-3 weeks
Kick off call with the client | 1d | Partner and Customer | Go through the project plan, resourcing and other details with customer
Requirements identification sessions (tags, taxonomies, entities, security) | 2d | Partner and Customer | Sessions to discuss how information can be structured around entities
Preparation for workshop by implementer + basic configuration | 4d | Partner | Run basic configuration on the environment as a prep for the main workshop
Analysis workshop (domain model + user stories + security + reporting + integration + migration strategy) | 3d | Partner and Customer | Showcase the WIP state of the config and run updates based on feedbacks
Requirements analysis and MVP Domain modeling | 3d | Partner | Finalize the scope definition for MVP roll-out including all dimensions of the project
Sign-off scope | 1d | Customer | Sign-off scope as final deliverable
1 - Configure - 1-2 weeks
Domain model configuration | 3d | Partner | Build final config for MVP launch
Details pages configuration | 3d | Partner | Configure search, and detail pages for exposing the content to CH users
Media rendition configuration | 1d | Partner | Set media renditions and transformation for public link needs
Delivery to client for initial testing | 1d | Partner and Customer | On-board customers to environment to run basic tests by asset upload, tagging, download etc.
2 - Client specific business logic - 1-3 weeks
User and usergroups security + SSO | 3d | Partner | Setup user groups for authorization, and SSO for authentication (if needed)
Workflows setup (if needed) | 2d | Partner | Setup workflows for product and asset entities for extending OOTB approval flow
Integrations with other systems (triggers, actions, custom code) | 5d | Partner | Assuming 2 simple integrations to be executed on certain events's trigger on CH.
Styling implementation (CSS, favicon etc) | 1d | Partner | Build CSS and color themes on the app based on brand guidelines from customer
Bug fixing | 2d | Partner and Customer | As customer is on the environment, run some bug fixing based on issues reported
3 - Migration - 1-3 weeks (if needed)
Migration template build (if needed) | 1d | Partner | If migration is needed, build the excel template to import assets
Migration template filling with right data | 6d | Partner and Customer | Filling the migration template with right metadata and accessible URLs to the images
Migration and quality checks on migrated assets | 4d | Partner and Customer | Import of 50K assets filled in migration template. Assets can be of images, videos and documents
4 - Code and Config promotion (if non-prod environments exist)
CLI setup for configuration management and promotion | 3d | Partner | Using CI/CD pipelines to manage and promote configs across environments
Promotion of configs from Dev to Staging | 2d | Partner | Initial promotion of config, testing, and validation of changes
Promotion of configs from Staging to Prod | 1d | Partner | Business-as-usual promotion which runs on validated setup on previous step
5 - Handover for final EQA and Go Live - 1-2 weeks
Test and Bug fixing | 3d | Customer | Final testing of app by including additional stakeholders on the platform
Go Live | 1d | Partner and Customer | Go-live (mainly an announcement if there is no legacy system being taken down)

## Notes
# | Item | Status
1 | Interview questions for better business analysis | Done
2 | Project management deck | Needs update
3 | Project plan - DAM | Done
4 | Domain model template | Done
5 | Project plan - Content Operations | Not started